## risks & causes (free-flow)
# | Strategic Objective | Description | 1:M | Source | Addressed | Notes
| 1. World class science | wrong instrument, wrong time |  | Mafikeng 2013
| 1. World class science | Throughput (instrumentation, scope, etc) |  | Mafikeng 2013
| 1. World class science | Site degradation (eg. Fracking, wind turbines,etc.) |  | Mafikeng 2013
| 1. World class science | low impact publications |  | Mafikeng 2013
| 1. World class science | insufficient competitive intelligence |  | Mafikeng 2013
| 1. World class science | insufficient collaboration with radio and gamma |  | Mafikeng 2013
| 1. World class science | Inappropriate science proposals (science plan) |  | Mafikeng 2013
| 1. World class science | Catastrophic telescope failure |  | Mafikeng 2013
| 2. Promote SALT as a global flagship optical telescope | Poor community outreach |  | Mafikeng 2013
| 2. Promote SALT as a global flagship optical telescope | Loss of interest in SALT (Ineffective PR) |  | Mafikeng 2013
| 2. Promote SALT as a global flagship optical telescope | Insufficient PR at conferences |  | Mafikeng 2013
| 3. Ensure sustainability | Weak corporate govenance |  | Mafikeng 2013
| 3. Ensure sustainability | Loss of South African Government Support |  | Mafikeng 2013
| 3. Ensure sustainability | Loss of partners (loss of funding) |  | Mafikeng 2013
| 3. Ensure sustainability | loss of key leadership |  | Mafikeng 2013
| 3. Ensure sustainability | Lack of world-class science |  | Mafikeng 2013
| 3. Ensure sustainability | Lack of African engagement |  | Mafikeng 2013
| 3. Ensure sustainability | Ignorance of telescope time market |  | Mafikeng 2013
| 3. Ensure sustainability | Energy security |  | Mafikeng 2013
| 3. Ensure sustainability | Composition of Board (Decision makers and funders) |  | Mafikeng 2013
| 3. Ensure sustainability | Breakdown of relations with partners |  | Mafikeng 2013
| 3. Ensure sustainability | Accidents, lack of preparedness |  | Mafikeng 2013
| 3. Ensure sustainability | A funding strategy |  | Mafikeng 2013
| 4. Instrumentation development | Uncontrolled budget |  | Mafikeng 2013
| 4. Instrumentation development | No funding |  | Mafikeng 2013
| 4. Instrumentation development | Loss of key staff | 5 | Mafikeng 2013
| 4. Instrumentation development | Insufficient technical staff |  | Mafikeng 2013
| 4. Instrumentation development | Inappropriate board management |  | Mafikeng 2013
| 4. Instrumentation development | Foreign exchange fluctuations |  | Mafikeng 2013
| 5. Optimise Operations | Weak operations contract |  | Mafikeng 2013
| 5. Optimise Operations | Obsolescence of equipment |  | Mafikeng 2013
| 5. Optimise Operations | Loss of key staff | 4 | Mafikeng 2013
| 5. Optimise Operations | lack of optimal planning |  | Mafikeng 2013
| 5. Optimise Operations | Inappropriate staff |  | Mafikeng 2013
| 5. Optimise Operations | Inadequate documentation |  | Mafikeng 2013
| 6. Use SALT for Human Capital Development | Insufficient utilisation of international partners |  | Mafikeng 2013
| 6. Use SALT for Human Capital Development | Insufficient production of African and female astronomers |  | Mafikeng 2013
SAAO 2014
OPS Levy
African collaboration

## Rating Scales (hidden)
ControlTiming |  | Objectives
Preventative
Detective
Contingent
Effectiveness
Effective
Partially Effective
Ineffective
Non-Existent
Adequacy
Adequate
Adequate but over controlled
Partially adequate
Inadequate
Probability
01- Rare | 1
02- Unlikely | 2
03- Moderate | 3
04- Likely | 4
05- Common | 5
Contributing
Root
Direct
Latent
Impact
01- Insignificant | 1
02- Minor | 2
03- Moderate | 3
04- Major | 4
05- Critical | 5
RiskResponseOption
Terminate
Treat
Transfer
Tolerate
Status
In-Progress
Completed
Deferred
Overdue
Not Started
RiskResponse
Terminate
Treat
Transfer
Tolerate
StrategicGoals
1. Achieving world class science
2. Promote SALT as a global flagship optical telescope
3. Ensure sustainability
4. Instrumentation development
5. Optimise Operations
6. Use SALT for Human Capital Development

## Combined
Strategic Objectives | Risk # | Risk Owner | Something occurs… Risk | Leading to… Possible Consequence | Caused by… Perceived Contributing Factors | Controlled by… Controls per cause | Control Owner | Timing of Controls | Control Effectiveness | Control Adequacy (Holistic) | Inherent |  |  |  | Residual |  |  |  | Required Residual |  |  |  | Risk Response Option | Actions Plans | Action Plan Owner | Action Plan Tasks | Start Date | Due Date | Action Plan Status
[11 empty] | Impact | Likelihood | Risk Rating |  | Impact | Likelihood | Risk Rating |  | Impact | Likelihood | Risk Rating
1. Achieving world class science: publishing highly cited papers in front rank journals | 1 | SALT Board | Inability to respond to demands and changing trends in astronomy | Loss of reputation and/or stature (because of the production of sub-standard outputs) | Obsolete telescope or instrument suite | Instrument development roadmap within Strategic Plan | Sub-committee of Board (JH, LL) | Preventative | Ineffective | Partially adequate | 4 | 4 | 16 | High Risk | 4 | 3 | 12 | High Risk | 2 | 2 | 4 | Low Risk | Treat | Convene a Board sub-committee (JH, LL) to finalise the Strategic Plan, and compile an instrument development roadmap | Board sub-committee (JH, LL) | Finalize the Strategic Plan and compile the instrument development roadmap in close consultation with the Board. Estimate costs. | Board meeting May 2015 | Board meeting Nov 2015 | Discussions with Ops Teams on 28/9/15, 12/10/15 - StrategicPlan updated and forwarded to JH on 23/11/15 for comment and tabling at BM, Discussion session planned at Nov 15 Board meeting
3. Ensure sustainability: scientific, financial, development |  |  |  | Withdrawal or default of partners on ops levy payment | Failure to monitor the performance of the telescope | [18 empty] | At each Board meeting, there should be a review of the effectiveness of telescope (science, engineering, operations, development) as well as from the point of view of fund-raising activities | SALT Board | Standing item on Board agenda to discuss effectiveness of telescope and prospects for partner funding | Board meeting May 2015 | Every Board meeting | Plan has been implemented - regular feedback at Board Meetings
|  |  |  | Difficult to promote SALT in the absence of scientific outputs of sufficient impact | Acceptance of science proposals with a low impact outcome or compromised by poor telescope usage | Time Assignment Committees and users | Individual Partners | Preventative | Ineffective | [14 empty] | Working with TACs and users to ensure high quality proposals and effective telescope usage | Board sub-committee (JH, PV) | Implement communication program within consortium | Board meeting May 2015 | Board meeting Nov 2015 | Communicated at Science Conference and to TACs Jun 15, user group meeting planned for Dec 15
[26 empty] | Get multi-partner proposals going | Board meeting May 2015 | Board meeting May 2016
[5 empty] | Lack of a long term strategic plan | SALT Board | Board Chairperson | Preventative | Ineffective | [14 empty] | The development and implementation of an appropriate strategic planning framework, policy and guidelines. | Board sub-committee (JH, LL) | Determine and implement plans for achieving the strategic objectives | Board meeting May 2015 | Board meeting Nov 2015 | Action Plan started led by JH with LL, PV to assist
[5 empty] | Long lead times to develop instruments | SALT Board | Board Chairperson | Detective | Effective | [14 empty] | The development of a Programme Management framework, policy, strategy and guidelines. | SALT Business Manager | Develop a Programme Managament framework for core processes, including scope, time, cost, quality, comminication, risk and performance management | Board meeting May 2015 | Board meeting Nov 2015 | Model used by RvB on Tracker project - done and implemented
[6 empty] | Project Manager | Project specific | Preventative | Effective | [14 empty] | Implement the Programme Management framework | Project Manager | Implementation of the Programme Management Framework for all new projects | All new projects | Start of project | Awaiting implementation for all new projects
[5 empty] | Poor corporate governance practices | SALT Board | SALT Board | Preventative | partially effective | [14 empty] | Review and update of the governance and management structures for SALT. | Board Chair (MS) | Review and update of the Charter/TOR for the Board and other relevant committees | Board meeting Nov 2015 | Board meeting May 2016 | Deferred to 2015 Nov
[6 empty] | Companies Act/King III Report |  | Preventative | partially effective | [16 empty] | Review BEC constitution and chairpersonship | Board meeting Nov 2015 | Board meeting May 2016
[6 empty] | Operating Contract | NRF/SAAO Director | Preventative | partially effective | [16 empty] | Establishment or re-constitution of any new/revised committees | Board meeting Nov 2015 | Board meeting May 2016
[5 empty] | Inconsistent payment of annual subscriptions by some partners | Shareholder's agreement | SALT Board | Preventative | Partially Effective | [14 empty] | Follow-up on outstanding subscriptions | SALT Business Manager | Reporting of outstanding subscriptions to the Board | Completed | Completed | Report on outstanding contributions tabled at Nov 15 Board meeting
[25 empty] | SALT Business Manager | Follow-up of outstanding subscriptions | Completed | Completed | Report on outstanding contributions tabled at Nov 15 Board meeting
[5 empty] | Shortage of funding | SALT Board | SALT Board | Preventative | Partially Effec | [14 empty] | Fund-raising plan, marketing | Board sub-committee (EW, MS, NC, BC) | Fund-raising campaign by assisting existing partners to raise funds, and seeking new partners to buy shares or telescope time | Board Meeting May 2015 | Board Meeting Nov 2015 | Action Plan started led by EW, meeting held 27/10/15
[5 empty] | Competing with higher spec-ed instruments | Instrument development roadmap within Strategic Plan | Sub-committee of Board (JH, LL) | [16 empty] | Convene a Board sub-committee (JH, LL) to finalise the Strategic Plan, and compile an instrument development roadmap | Board sub-committee (JH, LL) | Finalize the Strategic Plan and compile the instrument development roadmap in close consultation with the Board. Estimate costs. | Board meeting May 2015 | Board meeting Nov 2015 | Discussions with Ops Teams on 28/9/15, 12/10/15 - StrategicPlan updated and forwarded to JH on 23/11/15 for comment and tabling at BM, Discussion session planned at Nov 15 Board meeting
[5 empty] | Telescope failure | Planned preventative maintenance programme | Technical Operations Manager | Preventative | Effective | [14 empty] | Effective implementation of preventative maintenance programme | Technical Operations Manager | Regular management review and reporting on maintenance programme | Completed | Completed
6. Use SALT for Human Capital Development: graduate student training, outreach to undergrads & schools, general public | 2 | SALT Board | Suboptimal utilisation of SALT (by partner countries) for Human Capital Development (HCD) | A decline in skilled resources (Science Technology Engineering & Mathmatics (STEM)) | Some partners not having a clear strategy/plan to utilise SALT for HCD | "Partner specific" | "Partner specific" | Preventative | Effective | Partially adequate | 5 | 4 | 20 | Extreme Risk | 5 | 2 | 10 | High Risk | 2 | 2 | 4 | Low Risk | Treat | Develop plans for HCD for each interested partner | Board sub-committee (GB, BC, NC, EW) Partner specific | Determine HCD needs of each Partner country | Board meeting Nov 2015 | Board meeting May 2016 | Initial discussions were started
1. Achieving world class science: publishing highly cited papers in front rank journals |  |  |  | The production of limited science outputs | [21 empty] | Identify areas in which SALT can be utilised for HCD needs | Board meeting Nov 2015 | Board meeting May 2016
3. Ensure sustainability: scientific, financial, development |  |  |  | Loss of support for SALT from stakeholders primarily interested in HCD (e.g. SA govt and science funders) | [21 empty] | Develop an implementation plan for the utilisation of SALT for HCD | Board meeting Nov 2015 | Board meeting May 2016
4. Instrumentation development: telescope capability, as well as better and more capable instruments | [25 empty] | Report on the utilisation of SALT for HCD | Board meeting Nov 2015 | Board meeting May 2016
5. Optimise Operations: science productivity maximized, downtime minimized |  |  |  |  | Under cross-utilisation of educational capacity of partners | None in place |  | n/a | n/a | [14 empty] | Development and implementation of a strategy for the optimal cross-utilisation of educational capacity of partners | Board sub-committee (GB, BC, NC, EW) | Report on educational capacity of partners | Board meeting Nov 2015 | Board meeting Nov 2016 | Initial discussions were started
[26 empty] | Determine and report on ways in which educational capacity of partners can be utilised | Board meeting Nov 2015 | Board meeting Nov 2016
[5 empty] | Limited financial support for HCD (Partners have to fund their own HCD initiatives) | "Partner specific" | "Partner specific" | n/a | n/a | [14 empty] | Partner hosting Board meeting has standing invitation to hold an outreach day associated with each Board meeting | Partner specific | Optional organization of outreach day associated with each Board meeting by hosting partner | Board meeting Nov 2015 | Board meeting Nov 2015 | Outreash day planned 10/11/15
3. Ensure sustainability: scientific, financial, development | 3 | SALT Board | Partners defaulting on financial obligations | Compromised operations of the telescope | Partners perceive that there is no return on investment (because scientists are unable to motivate for funds). | Reporting on metrics is a standing item on the BEC agenda | SALT Science Management | Preventative | partially effective | partially adequate | 4 | 3 | 12 | High Risk | 4 | 3 | 12 | High Risk | 2 | 2 | 4 | Low Risk |  | At each Board meeting, there should be a review of the effectiveness of telescope (science, engineering, operations, development) as well as from the point of view of fund-raising activities | SALT Board | Standing item on Board agenda to discuss effectiveness of telescope and prospects for partner funding | Board meeting May 2015 | Every Board meeting | Plan has been implemented - regular feedback at Board Meetings
1. Achieving world class science: publishing highly cited papers in front rank journals |  |  |  | Sub-standard scientific outputs | Poor quality / insignificant scientific programs / ineffective telescope usage | Reporting on metrics is a standing item on the BEC agenda | SALT Science Management | Preventative | partially effective | partially adequate | [13 empty] | Produce and publish an annual report (should report on the value-add and return on investment) | Board sub-committee (Anand, LL, DB, LC) | Compile an annual report from inputs from partners | Board meeting May 2015 | Board meeting Nov 2015 | 2013 Annual Report ready for publication, some inputs received for 2014 - in progress
5. Optimize Operations | [25 empty] | Publish an annual report | Board meeting May 2015 | Board meeting Nov 2015
4. Instrumentation development: telescope capability, as well as better and more capable instruments |  |  |  |  | Non-defaulting partners are unable to absorb covering the levy shortfall | None in place | [17 empty] | Fund-raising plan | Board sub-committee (EW, MS, NC, BC) | Fund-raising campaign by assisting existing partners to raise funds, and seeking new partners to buy shares or telescope time | Board Meeting May 2015 | Board Meeting Nov 2015 | Action Plan started led by EW, meeting held 27/10/15
3. Ensure sustainability: scientific, financial, development |  |  |  |  | Non-defaulting partners are unable to absorb increases in the operations levy | Annual Budget | SALT Board | [16 empty] | Manage the annual budget to stay within the financial means of the Board | SALT Board | Manage the annual budget to stay within the financial means of the Board | Board meeting May 2015 | Board meeting Nov 2015 | Budget for 2016/17 presented at Nov 15 Board meeting
6. Use SALT for Human Capital Development: graduate student training, outreach to undergrads & schools, general public |  |  |  |  | Changing economic conditions | Financial management (including reprioritisation of projects) | Business Manager | Preventative | partially effective | [14 empty] | Priority projects to be presented to the Board for approval | Business Manager | Present a report on the priority projects to the Board for approval | Board meeting Nov 2015 | Board meeting Nov 2015 | Report on priority projects and Budget tabled at Nov 15 Board Meeting for approval
[5 empty] | Acts of god (earthquakes, etc) | Insurance Policy |  | Corrective | partially effective | [14 empty] | Annual review of insurance Policy | Business Manager |  |  | Board meeting May 2016 | Insurance renewal meeting scheduled for Feb 2016
3. Ensure sustainability: scientific, financial, development | 4 | SALT Board | Partners withdrawing from the consortium | Sub-standard scientific outputs | Poor quality / insignificant scientific programs / ineffective telescope usage | Reporting on metrics is a standing item on the BEC agenda | SALT Science Management | Preventative | partially effective | partially adequate | 4 | 2 | 8 | Medium Risk | 4 | 1 | 4 | Low Risk | 2 | 1 | 2 | Low Risk | Treat | Produce and publish an annual report (should report on the value-add and return on investment) | Board sub-committee (Anand, LL, DB, LC) | Compile an annual report from inputs from partners | Board meeting May 2015 | Board meeting Nov 2015 | 2013 Annual Report ready for publication, some inputs received for 2014 - in progress
1. Achieving world class science: publishing highly cited papers in front rank journals |  |  |  | Reduced income | [21 empty] | Publish an annual report | Board meeting May 2015 | Board meeting Nov 2015
4. Instrumentation development: telescope capability, as well as better and more capable instruments |  |  |  |  | Acceptance of science proposals with a low impact outcome or compromised by poor telescope usage | Time Assignment Committees and users | Individual Partners | Preventative | Ineffective | [14 empty] | Working with TACs and users to ensure high quality proposals and effective telescope usage | Board sub-committee (JH, PV) | Implement communication program within consortium | Board meeting May 2015 | Board meeting Nov 2015 | Communicated at Science Conference and to TACs Jun 15, user group meeting planned for Dec 15
5. Optimise Operations: science productivity maximized, downtime minimized | [25 empty] | Get multi-partner proposals going | Board meeting May 2015 | Board meeting May 2016
6. Use SALT for Human Capital Development: graduate student training, outreach to undergrads & schools, general public |  |  |  |  | Partners unable to afford Ops costs | SALT Board | SALT Board | Preventative | Partially Effec | [14 empty] | Fund-raising plan | Board sub-committee (EW, MS, NC, BC) | Fund-raising campaign by assisting existing partners to raise funds, and seeking new partners to buy shares or telescope time | Board Meeting May 2015 | Board Meeting Nov 2015 | Action Plan started led by EW, meeting held 27/10/15
[5 empty] | Partners not receiving time on the telescope comensurate to their % shareholding | Bi-annual reporting on SALT Observing statistice (time allocation, usage and productivity) | SALT Science Staff | Preventative | partially effective | [14 empty] | Monitor the equitable distribution of science observations amongst partners | SALT Board | Provide guidance to SALT Operations to correct cases where there is a problem | Every Board meeting | Every Board meeting | Report tabled at Board Meeing Nov 15
[5 empty] | Deterioration of site (permanent/cyclical) | AGA Act |  | Preventative | partialy effective | [14 empty] | Protect the observing site | SAAO Director | Develop and promulgate AGA regulations, Implement monitoring of condition of Sutherland site | Board meeting May 2015 | Board meeting May 2016 | Action Plan started
5. Optimise Operations: science productivity maximized, downtime minimized | 5 | SALT Board | Loss of institutional knowledge | Sub-optimal operations | Loss of key staff | Succession planning | SAAO Director | Preventative | partially | partially adequate | 5 | 4 | 15 | High Risk | 5 | 3 | 10 | High Risk | 2 | 2 | 4 | Low Risk | Treat | Develop and implement a succession planning strategy (support by an implementation plan) | SAAO Director | Identify key staff and determine appropriate succession plan for each key staff member. Implement the plan | Board meeting May 2015 | Board meeting May 2016 | Action Plan started
1. Achieving world class science: publishing highly cited papers in front rank journals
3. Ensure sustainability: scientific, financial, development |  |  |  |  | Inadequate knowledge management | Document Management System | SALT Business Manager | Preventative | effective | [14 empty] | Provide report on company document management | SALT Business Manager | Provide report on company doc management | Board meeting May 2015 | Board meeting Nov 2015 | Regular back-up procedures in place
4. Instrumentation development: telescope capability, as well as better and more capable instruments | [6 empty] | SALT Operations Manager | Preventative | partially effective | [14 empty] | Provide report on engineering document management system | SALT Operations Manager | Provide report on engineering document management system | Board meeting May 2015 | Board meeting Nov 2015 | Formal document management system in operation
6. Use SALT for Human Capital Development: graduate student training, outreach to undergrads & schools, general public
5. Optimise Operations: science productivity maximized, downtime minimized | 6 | SALT Board | Reduced operational capacity | Sub-optimal operations | Long lead times to fill vacancies(scarce skill) | Succession planning | SAAO Director | Preventative | partially | partially adequate | 5 | 4 | 15 | High Risk | 5 | 3 | 10 | High Risk | 2 | 2 | 4 | Low Risk | Treat | Develop and implement a succession planning strategy (support by an implementation plan) | SAAO Director | Identify key staff and determine appropriate succession plan for each key staff member. Implement the plan | Board meeting May 2015 | Board meeting May 2016 | Action Plan started
1. Achieving world class science: publishing highly cited papers in front rank journals
3. Ensure sustainability: scientific, financial, development
6. Use SALT for Human Capital Development: graduate student training, outreach to undergrads & schools, general public
5. Optimise Operations: science productivity maximized, downtime minimized | 7 | SALT Board | Poor/mis-management | Inappropriate strategic direction | Lack of a long term strategic plan | SALT Board | Board Chairperson | Preventative | Ineffective | Partially adequate | 5 | 3 | 15 | High Risk | 5 | 2 | 10 | High Risk | 2 | 2 | 4 | Low Risk | Treat | The development and implementation of an appropriate strategic planning framework, policy and guidelines. | Board sub-committee (JH, LL) | Determine and implement plans for achieving the strategic objectives | Board meeting May 2015 | Board meeting Nov 2015 | Action Plan started led by JH with LL, PV to assist
1. Achieving world class science: publishing highly cited papers in front rank journals |  |  |  | Inefficiencies (long lead times for projects) |  | Project Manager | Project specific | Preventative | Effective | [14 empty] | Implement the Programme Management framework | Project Manager | Implementation of the Programme Management Framework for all new projects | All new projects | Start of project | Awaiting implementation for all new projects
3. Ensure sustainability: scientific, financial, development |  |  |  |  | Poor corporate governance practices | SALT Board | SALT Board | [16 empty] | Review and update of the governance and management structures for SALT. | Board Chair (MS) | Review and update of the Charter/TOR for the Board and other relevant committees | Board meeting Nov 2015 | Board meeting May 2016 | Deferred to Nov 2015
6. Use SALT for Human Capital Development: graduate student training, outreach to undergrads & schools, general public | [5 empty] | Companies Act/King III Report |  | Preventative | partially effective | [16 empty] | Review BEC constitution and chairpersonship | Board meeting Nov 2015 | Board meeting May 2016
[6 empty] | Operating Contract | NRF/SAAO Director | Preventative | partially effective | [16 empty] | Establishment or re-constitution of any new/revised committees | Board meeting Nov 2015 | Board meeting May 2016
3. Ensure sustainability: scientific, financial, development | 8 | SALT Board | SALT is not recognised as an internationally competitive optical telescope | Reduced demand for usage of SALT | Sub-optimal operations | Engineering operations review at every Board meeting | SALT Board | Preventative | Effective | Partially adequate | 4 | 4 | 16 | High Risk | 3 | 3 | 9 | Medium Risk | 2 | 2 | 4 | Low Risk | Treat | Corrective action to improve engineering operations | SALT Board Chairperson | Corrective action to improve engineering operations | Completed | Completed
6. Use SALT for Human Capital Development: graduate student training, outreach to undergrads & schools, general public |  |  |  |  | Sub-standard scientific outputs | Scientific results review at every Board meeting | SALT Board | Preventative | Effective | [14 empty] | Corrective action to increase quantity and quality of scientific results | SALT Board Chairperson | Corrective action to increase quantity and quality of scientific results | Completed | Completed
[5 empty] | Poor marketing of SALT | Marketing and Publicity drive | SALT Board | Preventative | Partially effective | [14 empty] | Develop and implement a publicity plan | Board sub-committee (TW, NC) | Develop and implement a publicity plan | Board meeting May 2015 | Board meeting Nov 2015 | Awaiting implementation
[5 empty] | Lack of strategic direction in enhancing the technological capabilities of SALT | Instrument development roadmap within Strategic Plan | Sub-committee of Board (JH, LL) | [16 empty] | Convene a Board sub-committee (JH, LL) to finalise the Strategic Plan, and compile an instrument development roadmap | Board sub-committee (JH, LL) | Finalize the Strategic Plan and compile the instrument development roadmap in close consultation with the Board. Estimate costs. | Board meeting May 2015 | Board meeting Nov 2015 | Discussions with Ops Teams on 28/9/15, 12/10/15 - StrategicPlan updated and forwarded to JH on 23/11/15 for comment and tabling at BM, Discussion session planned at Nov 15 Board meeting
4. Instrumentation development: telescope capability, as well as better and more capable instruments | 9 | SALT Board | SALT becomes an obsolete optical telescope | SALT is not recognised as an internationally competitive optical telescope | Stagnation (lack of will) of technological development | Instrument development roadmap within Strategic Plan | Sub-committee of Board (JH, LL) | Preventative | Ineffective | Partially adequate | 5 | 4 | 20 | Extreme Risk | 5 | 2 | 10 | High Risk | 2 | 1 | 2 | Low Risk | Treat | Convene a Board sub-committee (JH, LL) to finalise the Strategic Plan, and compile an instrument development roadmap | Board sub-committee (JH, LL) | Finalize the Strategic Plan and compile the instrument development roadmap in close consultation with the Board. Estimate costs. | Board meeting May 2015 | Board meeting Nov 2015 | Discussions with Ops Teams on 28/9/15, 12/10/15 - StrategicPlan updated and forwarded to JH on 23/11/15 for comment and tabling at BM, Discussion session planned at Nov 15 Board meeting
1. Achieving world class science: publishing highly cited papers in front rank journals |  |  |  | Collapse of the SALT consortium | Lack of strategic direction in enhancing the technological capabilities of SALT | Instrument development roadmap within Strategic Plan | Sub-committee of Board (JH, LL) | [16 empty] | Convene a Board sub-committee (JH, LL) to finalise the Strategic Plan, and compile an instrument development roadmap | Board sub-committee (JH, LL) | Finalize the Strategic Plan and compile the instrument development roadmap in close consultation with the Board. Estimate costs. | Board meeting May 2015 | Board meeting Nov 2015 | Discussions with Ops Teams on 28/9/15, 12/10/15 - StrategicPlan updated and forwarded to JH on 23/11/15 for comment and tabling at BM, Discussion session planned at Nov 15 Board meeting
3. Ensure sustainability: scientific, financial, development |  |  |  |  | Funding limitations | Development fund | SALT Board | Preventative | Partially effective | [14 empty] | Collection of outstanding development contributions | SALT Board | Annual follow-up of outstanding development fund contributions | Board meeting May 2015 | Board meeting Nov 2015 | Awaiting implementation
5. Optimise Operations: science productivity maximized, downtime minimized | [25 empty] | Initiate follow-up actions for non-paying partners | Board meeting May 2015 | Board meeting Nov 2015 | Awaiting implementation
6. Use SALT for Human Capital Development: graduate student training, outreach to undergrads & schools, general public |  |  |  |  | Shortage of funding | SALT Board | SALT Board | Preventative | Partially Effec | [14 empty] | Fund-raising plan, marketing | Board sub-committee (EW, MS, NC, BC) | Fund-raising campaign by assisting existing partners to raise funds, and seeking new partners to buy shares or telescope time | Board Meeting May 2015 | Board Meeting Nov 2015 | Action Plan started led by EW, meeting held 27/10/15
4. Instrumentation development: telescope capability, as well as better and more capable instruments | 10 | SALT Board | Delayed development, testing and/or commissioning of an instrument | Commissioning of obsolete instruments on SALT | Poor programme/project management of instrument development, testing and commissioning | BEC | Board Chairperson | Detective | Partially Effective | Partially adequate | 4 | 4 | 16 | High Risk | 3 | 3 | 9 | Medium Risk | 2 | 2 | 4 | Low Risk | Treat | The development of a Programme Management framework, policy, strategy and guidelines. | SALT Business Manager | Develop a Programme Managament framework for core processes, including scope, time, cost, quality, comminication, risk and performance management | Board meeting May 2015 | Board meeting Nov 2015 | Model used by RvB on Tracker project - done and implemented
1. Achieving world class science: publishing highly cited papers in front rank journals |  |  |  | Delayed scientific outputs |  | Project Manager | Project specific | Preventative | Partially Effective | [14 empty] | Implement the Programme Management framework | Project Manager | Implementation of the Programme Management Framework for all new projects | All new projects | Start of project | Awaiting implementation for all new projects
3. Ensure sustainability: scientific, financial, development |  |  |  | Budget overrun
5. Optimise Operations: science productivity maximized, downtime minimized
6. Use SALT for Human Capital Development: graduate student training, outreach to undergrads & schools, general public
Note on C1: Pata: person or entity with the accountability and authority to manage the risk
Note on D1: Pata: uncertain event
Note on E1: Pata: what will the consequence (impact) be if the risk materialises
Note on F1: Pata: an event and or issue that may cause the risk to materialise
Note on G1: Pata: the means used to manage the risk, e.g. a policy, procedure, device, system, or any other action that acts to limit uncertainty in the achievement of objectives and/or ensure compliance with the law
Note on H1: Pata: Official responsible for the control
Note on I1: Pata: refers to the nature of the control, is it preventative and therefore would reduce the likelihood of a risk materialising or is it detective in that it reduces the impact of the risk should it materialise
Note on J1: Pata: By assessing the control effectiveness, management is providing an opinion relating to whether the controls are achieving their intended purpose. Rating done per control
Note on K1: Pata: By assessing the control adequacy, management gives their opinion on whether the design of the controls implemented to manage a risk is appropriate / adequate. Control adequacy is based on the combination of controls and how adequately the combination of controls mitigates the risk. It is therefore captured at the risk level rather than a control adequacy per control
Note on L1: Pata: Inherent risk rating is determined in the absence of all existing controls.
Note on P1: Pata: Residual risk rating is determined taking into account all existing controls, their timimng, effectiveness and adequacy.
Note on T1: Pata: Required residual risk rating is determined to ensure that the risk is mitigated to withing the organisation's risk appetite.
Note on X1: Pata: Terminate: steps taken to preventthe occurrence of
Note on Y1: Pata: articulate the planned risk treatment, in line with the selected risk response option.
Note on Z1: Pata: person or entity assigned accountability and authority to manage the development and implementation of the action plan. Also responsible for reporting on the status of implementation of the action plan.
Note on AA1: Pata: Key deliverables per action plan

## Sheet6 (hidden)
Strategic Objectives | Risk # | Risk Owner | Something occurs… Risk | Leading to… Possible Consequence | Caused by… Perceived Contributing Factors | Controlled by… Controls per cause | Control Owner | Timing of Controls | Control Effectiveness | Control Adequacy (Holistic) | Inherent |  |  |  | Residual |  |  |  | Required Residual |  |  |  | Risk Response Option | Actions Plans | Action Plan Owner | Action Plan Tasks | Start Date | Due Date
[11 empty] | Impact | Likelihood | Risk Rating |  | Impact | Likelihood | Risk Rating |  | Impact | Likelihood | Risk Rating
[13 empty] | 0 | Low Risk |  |  | 0 | Low Risk |  |  | 0 | Low Risk | Terminate
Note on C1: Pata: person or entity with the accountability and authority to manage the risk
Note on D1: Pata: uncertain event
Note on E1: Pata: what will the consequence (impact) be if the risk materialises
Note on F1: Pata: an event and or issue that may cause the risk to materialise
Note on G1: Pata: the means used to manage the risk, e.g. a policy, procedure, device, system, or any other action that acts to limit uncertainty in the achievement of objectives and/or ensure compliance with the law
Note on H1: Pata: Official responsible for the control
Note on I1: Pata: refers to the nature of the control, is it preventative and therefore would reduce the likelihood of a risk materialising or is it detective in that it reduces the impact of the risk should it materialise
Note on J1: Pata: By assessing the control effectiveness, management is providing an opinion relating to whether controls are achieving their purpose. Rating done per control
Note on K1: Pata: By assessing the control adequacy, management gives their opinion on whether the design of the controls implemented to manage a risk is appropriate / adequate. Control adequacy is based on the combination of controls and how adequately the combination of controls mitigates the risk. It is therefore captured at the risk level rather than a control adequacy per control
Note on L1: Pata: Inherent risk rating is determined in the absence of all existing controls.
Note on P1: Pata: Residual risk rating is determined taking into account all existing controls, their timimng, effectiveness and adequacy.
Note on T1: Pata: Required residual risk rating is determined to ensure that the risk is mitigated to withing the organisation's risk appetite.
Note on X1: Pata: Terminate: steps taken to preventthe occurrence of
Note on Y1: Pata: articulate the planned risk treatment, in line with the selected risk response option.
Note on Z1: Pata: person or entity assigned accountability and authority to manage the development and implementation of the action plan. Also responsible for reporting on the status of implementation of the action plan.
Note on AA1: Pata: Key deliverables per action plan